## Task Tracker
SDV QCar2 Autonomous Vehicle Project — Task Tracker
Day / Sprint | Module / Area | Task Description | Status | Outcome / Result | Blocker / On-Hold Reason | Next Action
Day 1 | OCR / Perception | OCR running on full frame — noisy detections. Implemented center ROI crop (60% of frame). Added confidence threshold 0.55. Integrated OCR output into YOLO debounce counter. | Completed | OCR detections reliable; both YOLO and OCR feed unified det_counter state machine. |  | Baseline for sign detection established
Day 1 | State Machine | Traced and validated MOVE_FORWARD / TURN_LEFT / TURN_RIGHT / STOPPED transitions. Confirmed permanent stop on stop-sign detection. | Completed | State transitions validated correct across all four states. |  | Document state diagram for team reference
Day 1 | Parameter Tuning | Set and tested detection confidence thresholds, sign distance ranges, trigger frame counts, turn duration parameters. | Completed | Parameters tuned; car responds at correct distance and with correct timing. |  | Revisit after track change
Day 1 | Latency Analysis | Identified high end-to-end latency from depth camera processing and OCR. Documented as known issue. Reduced OCR frequency to once every 5 frames. | On Hold | OCR latency partially reduced. Full fix requires TensorRT. | TensorRT optimization not yet started — dependent on finalising model pipeline first. | Implement TensorRT for YOLO (5–10x speedup expected)
Day 2 | System Audit | Full hardware/software audit of QCar2. Confirmed: Jetson AGX Orin, JetPack R35.6, 30GB RAM, CUDA 11.4, Ubuntu 20.04, ROS2 Humble, Quanser qcar2-autonomy installed, Autoware present. | Completed | Baseline system state fully documented. |  | Keep audit doc updated
Day 2 | PyTorch CUDA Fix | PyTorch 2.4.1 was CPU-only build — GPU not accessible. Removed CPU build. Installed NVIDIA-official Jetson-optimised PyTorch wheel compiled against CUDA 11.4 / ARM. | Completed | torch.cuda.is_available() returns True. YOLOv8 inference on GPU confirmed. |  | Pin version in requirements to prevent pip overwrite
Day 2 | Torchvision Source Build | Standard pip torchvision not compatible with ARM/aarch64. Built torchvision v0.16.0 from source on Jetson with all build dependencies. Build time ~15 min. | Completed | torchvision installed and compatible with Jetson PyTorch. |  | Document exact build commands in README
Day 2 | CUDA PATH Fix | nvcc not resolving — CUDA binary/library dirs absent from PATH and LD_LIBRARY_PATH. Added correct CUDA 11.4 paths. | Completed | nvcc resolves correctly. CUDA libraries accessible system-wide.
Day 2 | .bashrc Repair | Broken .bashrc entries pointing to non-existent ROS2 workspace paths. Removed incorrect lines using sed. Verified and rewrote with correct paths: /opt/ros/humble, Quanser workspace, custom ROS2 workspace. | Completed | New terminals open without errors. All source commands work.
Day 2 | pip Constraint File | pip dependency resolver was overwriting Jetson PyTorch with CPU-only build during other package installs. Created pip constraint file pinning PyTorch to Jetson-compatible version. | Completed | PyTorch version protected across future pip installs. |  | Include in onboarding docs
Day 2 | Jetson Performance Mode | Set Jetson AGX Orin to maximum performance mode — all CPU cores unlocked, GPU clock maximised, power throttling removed. | Completed | Inference latency reduced directly. |  | Confirm mode persists after reboot
Day 2 | Sensor Verification | Sourced Quanser workspace. Confirmed live: LiDAR /scan, IMU /qcar2_imu, Odometry /odometry/filtered, Map /map, Battery /qcar2_battery, Nav2 stack active. | Completed | All sensors except camera confirmed live. Nav2 full stack active.
Days 3–6 | RealSense Activation | Launched RealSense D435 via Quanser rgbd node. Confirmed /camera/color_image (1280x720 BGR8) and /camera/depth_image active. | Completed | RealSense established as primary perception camera unblocking all further development. |  | Use as fallback even after CSI fix
Days 3–6 | CSI Camera Investigation — 11 Attempts | Systematic diagnosis of CSI failure. Attempts: Quanser ROS2 node all resolutions, PAL Camera2D direct, QCarCameras class, IMX219 kernel module load, device tree overlay, EGL display fix, GStreamer pipeline, OpenCV V4L2, v4l2-ctl raw capture, QUARC camsock socket, Probe/Observer local. | On Hold | Root cause confirmed: /dev/camera/ device nodes absent. Stock JetPack missing Quanser custom camera middleware layer. IMX219 sensors physically present and kernel-bound but cannot stream. | Requires Quanser custom JetPack image to create /dev/camera/ device nodes. Stock NVIDIA JetPack does not include this layer. Escalation to Quanser support recommended. | Request Quanser custom JetPack image from vendor. Workaround: connect physical HDMI monitor.
Days 3–6 | Camera Bridge Node | Wrote camera_bridge.py ROS2 node in sdv_perception package. Opens all 4 CSI cameras via Camera2D with 2s stagger. Publishes to /sdv/camera/front¦left¦rear¦right. RealSense topics published in parallel. | Completed | Topics active. CSI topics blank (driver issue). RealSense topics valid. CSI frame rate ~0.3–0.5fps (hardware driver blocking — not threading issue). |  | Update once CSI driver resolved
Day 7 | Deep Library Analysis — libquanser_media.so | Full binary analysis of libquanser_media.so. Identified Argus path and V4L2 path. Traced eglGetDisplay dependency through libnvargus_socketclient.so. Confirmed library attempts Argus first, no automatic V4L2 fallback for CSI. | Completed | Root cause of headless failure fully understood at library level. Documented for team. |  | Share findings with Quanser support ticket
Day 7 | EGL Fake Preload Attempt | Compiled fake EGL shared library in C returning non-null from eglGetDisplay and eglInitialize. Preloaded via LD_PRELOAD. Argus session creation failed at deeper EGL validation — stub incomplete. | On Hold | Approach abandoned — increasing complexity without clear path. | Argus performs additional EGL validation beyond initial display handle. Full EGL stub implementation not feasible without Argus source code. | Deprioritised. HDMI dongle workaround confirmed effective.
Day 7 | HDMI Monitor Workaround Confirmed | Physically connected HDMI monitor to QCar2. All 4 CSI camera windows opened and displayed output. Conclusively confirmed: failure is EGL display context dependency, not hardware/driver issue. | Completed | CSI cameras fully functional with physical HDMI. Workaround documented. |  | Use dummy HDMI dongle as permanent fix
Day 8 | Torchvision NMS / C++ Ops Fix | torchvision.ops.nms() failing — CPU-only pip build in .local conflicting with system build. Removed both. Rebuilt torchvision v0.16.0 from source with FORCE_CUDA=1 and CUDA_HOME=/usr/local/cuda-11.4. | Completed | GPU-accelerated NMS operational. YOLOv8 post-processing runs on GPU.
Day 8 | SDV Perception ROS2 Package v2.0 | Built and launched full sdv_perception ROS2 package. Integrated: YOLOv8 GPU inference, RealSense depth fusion (pinhole model, per-detection 3D distance), lane detection (HLS, BEV warp, polynomial fit), LiDAR front 60° cone processor. Outputs: /sdv/perception/detections, /lane, /threat, /annotated. | Completed | First live result: 3 detections (person 95% @ 1.0m, person 63% @ 0.7m). FPS: 2.1. Latency: 37.4ms. Full GPU pipeline confirmed operational. |  | Optimise FPS via TensorRT next
Days 9–11 | Lane Detection — RealSense Pipeline | Built lane detection on RealSense RGB: HLS color space, color masking, ROI trapezoid, bird's-eye perspective warp, histogram base detection, 9-window sliding window search, 2nd-degree polynomial fit with 8-frame EMA smoothing. Published to /sdv/perception/lane. | Completed | Lane offset published and consumed by control node.
Days 9–11 | CSI Camera Fix — EGL Headless (FINAL) | Identified two-part fix: (1) dummy HDMI dongle physically connected — GPU initialises proper hardware context; (2) os.environ.pop(DISPLAY) + os.environ.pop(XAUTHORITY) before QCarCameras() — forces nvarguscamerasrc to headless NVMM allocation; restore DISPLAY after init for OpenCV. Applied to camera_bridge.py and all standalone scripts. | Completed | All 4 CSI cameras streaming at 820x616 @ 30fps (up to 80fps). All frame max pixel values non-zero. Fix validated with saved .jpg frames. |  | Fix is permanent — documented in all scripts
Days 9–11 | Lane Detection Modular Package — 20 Files | Rebuilt lane detection as proper Python package: config.yaml, config_loader.py (hot-reload via mtime+SIGHUP), camera_capture.py (20-frame warmup, timestamps), preprocessor.py (undistort, resize, adaptive HSV, ROI, BEV warp), lane_detector.py (sliding window, warm-start, RANSAC poly fit, stop line HoughLinesP, traffic hook, width consistency check), metrics.py (curvature, lateral offset), controller.py (PID + Stanley, speed-adaptive gains, IMU dead reckoning 2s fallback), logger.py, visualizer.py, main.py. Tools: health_check.py, tune_hsv.py, calibrate_camera.py, calibrate_perspective.py. | Completed | 22/22 unit tests passing (7 config, 9 metrics, 6 preprocessor). Full pipeline tested on sample track image. |  | Deploy to Jetson; run calibration scripts on actual track
Days 9–11 | Yellow Tape HSV Calibration | Measured actual HSV of yellow tape on black surface: H≈37, S≈30, V≈86 — far below standard yellow saturation (S>100). Widened thresholds to H:10–45, S:10–180, V:40–200. Added adaptive V-channel compensation scaling min_V with frame mean brightness. | Completed | Detection reliability improved significantly under lab lighting. |  | Re-measure HSV under different lighting conditions on actual track
Days 9–11 | Perspective Calibration Tool | Built calibrate_perspective.py — live frame capture, manual vertex adjustment with real-time BEV preview, saves verified values to config.yaml. Built calibrate_camera.py for lens undistortion matrix. | Completed | Calibration repeatable without code changes. BEV calibration verified. |  | Run on actual track floor before autonomous test
Days 9–11 | RANSAC Polynomial Fitting | Replaced simple numpy polyfit with RANSAC implementation (no sklearn — built from scratch with numpy). 100 trials, min 10 samples, residual threshold 2.0px, early exit at 80% inliers, refine on inliers, fallback to polyfit if RANSAC fails. | Completed | Substantially more robust to reflection noise and outlier pixels vs simple polyfit.
Days 9–11 | LiDAR Hardware Stop Fix | LiDAR motor continued spinning after Ctrl+C. Error -10 on next init. Integrated Quanser hardware_stop.py pattern: explicitly init new QCarLidar() and call .terminate() on exit, plus QCar().terminate(). Applied to all shutdown paths. | Completed | LiDAR stops correctly on program exit. Error -10 no longer occurs on restart.
Days 9–11 | FPS Optimisation — Resolution Reduction | Pipeline at 2.1fps, target 15fps. Reduced YOLO imgsz from 1280 to 416. Camera output reduced to 640x360. FP16 half-precision confirmed active. | In Progress | FPS improved from 1.9 to 4.2fps (2x). Target 15fps not yet reached. | TensorRT optimisation required for further gains (expected 3–5x on Orin). | Implement TensorRT engine conversion for YOLOv8
Day 12 | Real-Time Telemetry Dashboard | Built full SDV telemetry dashboard: HTML/CSS/JS frontend + FastAPI async backend. Displays: all 4 CSI camera MJPEG streams (30fps), RealSense depth colormap (COLORMAP_JET, 320x240 for encoding speed), RPLiDAR 2D polar plot with Canvas API (360 scan points, distance rings at 0.5m, closest object XY coordinates highlighted), battery % bar, steering angle SVG arc gauge. Tiered update: cameras continuous, LiDAR 10Hz JSON poll, telemetry 5Hz JSON poll. | Completed | All sensors visible simultaneously in browser over local network. Accessible from dev laptop — no extra software needed. |  | Add lane detection overlay panel; add FPS counter per camera

## On Hold & Blocked
SDV QCar2 — On Hold / Blocked Items
Task ID | Module | Description | Root Cause of Block | Justification for Hold | Impact if Unresolved | Resolution Path | ETA
T-004 | Latency / YOLO | End-to-end pipeline latency high — OCR and depth processing primary contributors. OCR frequency reduced to 1/5 frames as interim fix. | TensorRT engine not yet compiled. Model pipeline still in active development — premature to lock model for TensorRT. | Partial fix (OCR frequency reduction) applied. Full fix requires stable final model. | FPS stays below 15fps target — limits real-time obstacle avoidance responsiveness. | Convert YOLOv8 to TensorRT INT8/FP16 engine using trtexec on Jetson. Expected 3–5x speedup. | Post lane-following stabilisation
T-014 | CSI Camera — Custom JetPack | CSI cameras require Quanser custom JetPack image to create /dev/camera/ device nodes. 11 software approaches all failed. Stock JetPack missing Quanser camera middleware layer. | Quanser custom JetPack not available on this unit. Device nodes absent. EGL dependency in libquanser_media.so blocks headless streaming entirely without them. | Workaround established (HDMI dongle + env var strip) — CSI cameras now functional for development. Custom JetPack needed only for production headless deployment. | For field deployment without HDMI dongle, CSI cameras will not stream. Limits surround-view capability in headless mode. | Raise support ticket with Quanser requesting custom JetPack image or documentation for creating device nodes on stock JetPack. | Pending Quanser vendor response
T-017 | EGL Fake Preload | Fake EGL library preloaded via LD_PRELOAD to bypass display requirement. Argus session failed at deeper EGL validation beyond initial display handle. | Argus performs multi-level EGL validation. Implementing complete EGL stub requires reverse engineering undocumented Argus internals. | Workaround (HDMI dongle) is simpler, reliable, and already working. Continuing fake EGL adds risk with no guaranteed result. | No impact — HDMI workaround covers all current use cases. | Deprioritised. Revisit only if HDMI workaround becomes unacceptable for deployment. | Deprioritised indefinitely
T-028 | FPS Optimisation | Current 4.2fps below 15fps target. Resolution reduction applied (partial gain). TensorRT conversion not yet started. | TensorRT requires finalised, stable model. Current pipeline still being tuned. Premature engine compilation would need redo after each model change. | 4fps sufficient for current slow-speed lab testing and calibration phase. Production speed not yet required. | Insufficient FPS for high-speed autonomous driving or real-time obstacle avoidance at track speeds. | 1. Convert YOLOv8n to TensorRT FP16 engine. 2. Profile per-module to identify secondary bottleneck. 3. Consider frame-skip for lane detection (lower update rate acceptable for steering). | After lane following stable on track

## Upcoming Plans
SDV QCar2 — Upcoming Plans & Roadmap
Phase | Task ID | Planned Task | Objective | Approach / Method | Dependencies | Expected Outcome | Priority | Planned Sprint
Phase 1 — Perception | P-001 | TensorRT optimisation for YOLOv8 | Increase pipeline FPS from 4.2 to 15+ fps for real-time autonomous driving. | Export YOLOv8n to ONNX. Convert to TensorRT engine using trtexec with FP16 precision on Jetson Orin. Replace PyTorch inference call with TensorRT runtime in perception node. | Stable final YOLOv8 model; no further architecture changes. | 3–5x inference speedup. Expected 12–20fps on Orin. | Critical | Next Sprint
Phase 1 — Perception | P-002 | Lane following autonomous run on actual track | Complete one full autonomous lap on the yellow tape track with PID steering. | Run calibration scripts on actual track floor. Tune HSV thresholds for track lighting. Adjust BEV perspective. Tune PID gains at target speed. Monitor via telemetry dashboard. | CSI camera operational (done). Perspective calibration tool (done). Track access. | Car completes lap staying within lane boundaries. | Critical | Next Sprint
Phase 1 — Perception | P-003 | IMU dead reckoning validation | Validate 2-second IMU fallback holds correct heading when lane detection temporarily lost. | Intentionally cover part of lane. Measure heading drift against ground truth. Tune IMU integration alpha. | IMU /qcar2_imu topic confirmed live. | Smooth lane re-acquisition after brief occlusion. | High | Next Sprint
Phase 1 — Perception | P-004 | Stop line and intersection detection | Detect stop lines and intersections on the track to enable intersection behaviour. | HoughLinesP on BEV binary image (already in lane_detector.py). Add confidence threshold. Trigger state machine STOPPED_AT_INTERSECTION state. | Lane detection pipeline operational. | Car stops at stop lines and waits before proceeding. | High | Sprint +1
Phase 1 — Perception | P-005 | Traffic sign detection and response integration | Car reads traffic signs (stop, speed limit, turn, no-entry, pedestrian) and changes behaviour accordingly. | YOLOv8 detection (already working) + EasyOCR fallback (already working). Map detected class to state machine action. Test at different distances and angles. | YOLOv8 on GPU (done). State machine (done). Sign dataset for specific signs used on track. | Car responds correctly to all 5 sign types at varying distances and angles. | High | Sprint +1
Phase 1 — Perception | P-006 | Obstacle avoidance — path around permanent obstacle | If obstacle does not clear within timeout, calculate and execute path around it. | After resume countdown (5 frames), if obstacle still present, trigger path re-planning. Use LiDAR map and simple geometric detour calculation. Execute steering sequence to go around and re-acquire lane. | LiDAR operational (done). Lane following stable. | Car avoids permanent obstacles and returns to lane. | High | Sprint +2
Phase 2 — SLAM | P-007 | SLAM map building on track | Build persistent map of the track for localisation and path planning. | Use rf2o_laser_odometry (already installed) + /odometry/filtered EKF. Launch slam_toolbox or Cartographer. Drive track manually to build map. Save map. | LiDAR, IMU, odometry all confirmed live. SLAM packages present on system. | Saved .pgm map of track available for Nav2 path planning. | High | Sprint +2
Phase 2 — SLAM | P-008 | Nav2 autonomous navigation integration | Use Nav2 stack (already active on system) to navigate from point A to point B on saved map. | Load saved SLAM map into Nav2 map server. Set 2D pose estimate. Send 2D nav goal. Verify Nav2 generates and follows global path. | SLAM map (P-007). Nav2 stack already active on system. | Car navigates A to B autonomously using Nav2. | High | Sprint +3
Phase 3 — ADAS | P-009 | Speed adaptation based on sign detection | Car automatically reduces speed at speed limit signs and near pedestrian crossings. | Map detected speed limit value from OCR to target throttle. Scale PID base throttle accordingly. Speed-adaptive gain scheduling already in controller. | Sign detection working (T-001, T-005). Controller speed-adaptive gains already implemented. | Car slows correctly at speed limit and pedestrian signs. | Medium | Sprint +3
Phase 3 — ADAS | P-010 | Full course integration test | Complete full course with lanes, traffic signs, obstacles, and intersections all active simultaneously without human intervention. | Integrate all modules. Run end-to-end test. Log all failures. Fix and retest. | All Phase 1 and 2 tasks complete. | Car completes full course autonomously. | Critical | Sprint +4
Phase 4 — Optimisation | P-011 | Dashboard enhancements | Add lane detection overlay, per-camera FPS counter, detection event log, and alert panel to telemetry dashboard. | Add /sdv/perception/annotated stream to dashboard. Add JS event log panel. Add alert styling for low battery and obstacle detected. | Dashboard operational (T-029). | Richer real-time monitoring for demos and debugging. | Medium | Sprint +2
Phase 4 — Optimisation | P-012 | Digital Twin setup | Set up digital twin environment for simulation testing and demo for upcoming visits. | To be defined by team lead. Likely RViz2 or Gazebo-based visualisation of QCar2 sensor data. | Instructions from team lead (pending). | Digital twin running and ready for demo. | High | TBD — awaiting team lead brief
Phase 4 — Optimisation | P-013 | FANUC Arm demo setup | Set up and maintain FANUC Arm demo for upcoming visits. | To be defined by team lead. | Instructions from team lead (pending). | FANUC Arm demo ready for visitor presentation. | High | TBD — awaiting team lead brief

## Models & Datasets
SDV QCar2 — Models, Datasets & External References
Reference Name | Type | Version / Source | Purpose in Project | Where Used | Licence / Notes | Local Path on Jetson | Status
YOLOv8n | Pre-trained model | Ultralytics YOLOv8 v8.2.101 — yolov8n.pt (nano, COCO-pretrained) | Real-time object detection: traffic signs, persons, vehicles, obstacles. GPU inference on Jetson Orin. | sdv_perception ROS2 node, sdv_lane_follower.py, sdv_autonomous.py | AGPL-3.0 licence. Model weights downloaded from Ultralytics GitHub releases. | ~/Desktop/SDV_workspace/models/yolov8n.pt | Active — in use
YOLOv8n-seg | Pre-trained model | Ultralytics YOLOv8 v8.2 — yolov8n-seg.pt (segmentation variant) | Tested for lane segmentation approach. COCO classes do not include lane markings — approach not viable without custom training. | test_yolo_lane.py (evaluation only) | AGPL-3.0 licence. | ~/Desktop/SDV_workspace/models/yolov8n-seg.pt | Evaluated — not used for lane detection
EasyOCR | Pre-trained OCR model | JaidedAI EasyOCR — English language model | Traffic sign text reading fallback when YOLO class not sufficient. Reads speed limit numbers, directional text. | OCR detection module, integrated into det_counter with YOLO (Task T-001) | Apache 2.0 licence. Model weights auto-downloaded on first use. | /home/nvidia/.EasyOCR/model/ | Active — in use at 1/5 frame frequency
COCO Dataset | Training dataset (reference) | MS COCO 2017 — 80 object classes | YOLOv8n was pre-trained on COCO. Provides detection capability for person, car, traffic light, stop sign etc. | Underpins YOLOv8n inference. Not stored locally — model weights encode knowledge. | Public dataset. cocodataset.org | Not stored locally | Reference only
TuSimple Lane Dataset | Dataset (reference for future) | TuSimple benchmark dataset — highway lane detection | Reference architecture for sliding window and polynomial fitting pipeline design. Not used for training. | Pipeline design reference for lane_detector.py | TuSimple benchmark licence. https://github.com/TuSimple/tusimple-benchmark | Not stored locally | Reference only — future fine-tuning candidate
CULane Dataset | Dataset (reference for future) | CULane benchmark — urban driving lane detection, 9 categories including curves, crowded scenes, shadows | Reference for CondLaneNet-style architecture. Evaluated but not used due to training data requirements. | Evaluated during approach selection for lane detection | https://xingangpan.github.io/projects/CULane.html | Not stored locally | Reference only — future training data candidate
CondLaneNet | Architecture reference | ICCV 2021 — Conditional Convolution lane detection. ResNet-18 small: 220FPS F1=78.14 | Evaluated as deep learning alternative to classical CV lane detection. Not adopted due to lack of custom training data for our track. | Approach evaluation — not deployed | https://arxiv.org/abs/2105.05003 AGPL licence | Not stored locally | Evaluated — not deployed. Future candidate if training data collected.
Quanser PAL Library | Hardware SDK | Quanser PAL (Platform Abstraction Layer) — Python. Version: qcar2-autonomy package. | Hardware interface for QCar2: QCar (motor control), QCarCameras (CSI), QCarLidar, Camera2D. Core dependency for all hardware access. | All hardware interface code. car.write(), QCarLidar().terminate(), QCarCameras() | Proprietary — Quanser licence. Part of qcar2-autonomy package. | /home/nvidia/Documents/Quanser/0_libraries/python/pal/ | Active — critical dependency
PyTorch | Deep learning framework | NVIDIA Jetson-optimised build v2.1.0a0+41361538.nv23.06 — compiled for CUDA 11.4 / ARM aarch64 | GPU tensor operations underpinning YOLOv8 inference on Jetson Orin. | YOLOv8 inference pipeline | BSD licence. Source: NVIDIA NGC / Jetson distribution servers. | /home/nvidia/.local/lib/python3.8/site-packages/torch/ | Active — pinned via pip constraint file
torchvision | Deep learning library | v0.16.0 — compiled from source on Jetson with FORCE_CUDA=1, CUDA_HOME=/usr/local/cuda-11.4 | Provides torchvision.ops.nms() (GPU-accelerated non-maximum suppression) required by YOLOv8 post-processing. | YOLOv8 post-processing / NMS | BSD licence. Built from source: github.com/pytorch/vision tag v0.16.0 | /home/nvidia/.local/lib/python3.8/site-packages/torchvision/ | Active
Intel RealSense SDK (librealsense) | Sensor SDK | Intel RealSense D435 — integrated via Quanser qcar2_nodes ROS2 package (ros2 run qcar2_nodes rgbd) | Primary perception sensor: 1280x720 RGB @ 30fps + registered depth image. Used for YOLO detection, depth fusion, initial lane detection. | ROS2 topics: /camera/color_image, /camera/depth_image | Apache 2.0 licence. | Managed by qcar2_nodes ROS2 package | Active — primary camera sensor
FastAPI | Web framework | FastAPI (pip) + Uvicorn ASGI server | Async backend for real-time telemetry dashboard. Serves MJPEG streams and JSON telemetry endpoints. | Day 12 telemetry dashboard backend | MIT licence. pip3 install fastapi uvicorn | /home/nvidia/.local/lib/python3.8/site-packages/fastapi/ | Active — dashboard backend
OpenCV | Computer vision library | OpenCV 4.12.0 | All image processing: color space conversion, morphological ops, perspective transform, JPEG encoding, drawing functions. | preprocessor.py, lane_detector.py, visualizer.py, dashboard MJPEG encoding | Apache 2.0 licence. | System-installed | Active — core CV library

## Daily Summary
SDV QCar2 — Daily Work Summary
Day | Primary Objective | Key Tasks Completed | Key Issue Encountered | Resolution / Status | Pending / Next
Day 1 | OCR fix, state machine validation, parameter tuning, latency identification | Center ROI crop for OCR; confidence threshold 0.55; OCR integrated into YOLO det_counter; state machine validated; parameters tuned; OCR frequency reduced to 1/5 frames. | High end-to-end latency from depth processing and OCR. | Partial: OCR frequency reduced. Full fix requires TensorRT (on hold). | TensorRT optimisation; system audit
Day 2 | Full system audit and environment repair | PyTorch CUDA fix (Jetson wheel); torchvision source build; CUDA PATH fixed; .bashrc repaired; pip constraint file; Jetson max performance mode; all sensors confirmed live. | PyTorch CPU-only build — GPU not accessible. pip overwriting Jetson build during other installs. | Completed: Jetson PyTorch installed and pinned. All sensors confirmed. | CSI camera investigation; perception pipeline
Days 3–6 | CSI camera diagnosis; RealSense activation; camera bridge node | RealSense D435 confirmed live (primary camera); 11 CSI fix attempts; camera_bridge.py ROS2 node written; root cause confirmed as /dev/camera/ device nodes absent. | CSI cameras non-functional — all 11 fix approaches failed. Root cause: Quanser custom JetPack missing from this unit. | On hold — requires Quanser custom JetPack or HDMI workaround. RealSense established as primary camera. | Deep library analysis; perception pipeline development
Day 7 | Deep library analysis; HDMI workaround confirmed | Full libquanser_media.so analysis; EGL dependency chain traced; HDMI monitor connected — all 4 CSI cameras opened; fake EGL preload attempted and abandoned. | Fake EGL preload failed — Argus multi-level EGL validation not fully stubbed. | HDMI workaround confirmed effective. Dummy HDMI dongle identified as permanent solution. | Perception pipeline v2.0
Day 8 | Full Perception Pipeline v2.0 | Torchvision NMS C++ ops fixed (rebuilt from source FORCE_CUDA=1); sdv_perception ROS2 package built; YOLOv8+depth fusion+lane detection+LiDAR pipeline launched; first live detections. | Two conflicting torchvision installs — CPU build overriding GPU build. | Completed: Both removed; rebuilt from source; GPU NMS confirmed. First live result: 2.1fps, 37.4ms latency, detections with real-world distances. | Lane detection improvement; CSI camera final fix; FPS optimisation
Days 9–11 | Lane detection pipeline + CSI camera final fix | RealSense lane detection pipeline; CSI camera fixed (dummy HDMI + env var strip); 20-file modular lane package; RANSAC poly fitting; calibration tools; 22 unit tests passing; LiDAR hardware stop fixed. | Yellow tape HSV S≈30 (far below standard). Perspective miscalibration when moving from table to floor. LiDAR error -10 on restart. | Completed: Adaptive HSV thresholds; calibration tools built; hardware stop fixed. FPS at 4.2fps — TensorRT needed for 15fps. | Autonomous run on actual track; TensorRT; FPS optimisation
Day 12 | Real-time telemetry dashboard | FastAPI async backend; 4x CSI MJPEG streams; RealSense depth colormap stream; RPLiDAR 2D polar plot with closest object XY; battery % bar; steering angle SVG gauge. All sensors visible simultaneously in browser. | MJPEG encoding overhead at full depth resolution; LiDAR angle frame mismatch vs vehicle forward axis. | Completed: Depth frame resized to 320x240 (encoding <5ms); rotation transform applied for vehicle-frame LiDAR angles. | Add lane overlay panel to dashboard; FPS counter per camera; TensorRT; autonomous track run